## COMPANY NAME
Project Deadline Timetable
Company Name: | ABC Solutions Pvt. Ltd. |  |  | Task Completion % | Website Redesign |  | 100%
Department: | Customer Support
Period Covered: | 2025-01-01
Project Name | Task Description | Assigned To | Start Date | End Date | Status | Days Remaining | Comments | Task Completion Percentage: | Total Days of Task:
Website Redesign | Create Wireframes | Jane Doe | 2025-01-10 | 2025-01-20 | Completed | 0 | Completed ahead of time | 100 | 10
Mobile App Launch | Backend Development | John Smith | 2025-01-15 | 2025-02-16 | In Progress | 25 | On track | 50 | 32
Marketing Campaign | Design Ads | Sarah Lee | 2025-01-20 | 2025-01-31 | Not Started | 9 | Pending initial review | 0 | 11
Product Packaging | Finalize Design | Emily Clark | 2025-01-25 | 2025-02-05 | Not Started | 14 | Awaiting client approval | 0 | 11
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Formulas:
Days Remaining = IF([End Date]="","",IF([Status]="Completed", 0, DATEDIF(TODAY(), [End Date], "d")))
Total Days of Task: = DATEDIF([Start Date], [End Date], "d")