## Event Plannin Sheet
Event Planning Sheet
Event Information
Event Name |  | Event Coordinator
Event Date | 2024-11-01 | Number of Attendees
Event Time | 2024-11-01 22:04 | Event Theme
Event Location |  | Budget
1. Event Goals & Objectives
Define the primary goals and objectives of the event.
Goal 1:
Goal 2:
Objective 1:
Objective 2:
2. Budget Breakdown
Track estimated and actual costs for various aspects of the event.
Expense Category | Estimated Cost | Actual Cost | Notes
Venue Rental | 1200 | 1200
Catering/Food & Beverages | 800 | 1000
Entertainment
Marketing/Promotions
Equipment (AV, Lighting)
Transportation
Decorations
Staffing/Volunteers
Miscellaneous
Total | 2000 | 2200
3. Event Schedule
Provide a detailed timeline of the event from setup to breakdown.
Time | Activity | Responsibility
8:00 | Venue setup begins | Event Coordinator/Staff
9:30 | Audio-Visual (AV) equipment setup | AV Team
10:00 | Registration opens | Registration Team
10:30 | Welcome speech | Event Coordinator
11:00 | Keynote speaker presentation | Keynote Speaker
12:00 | Lunch break | Catering Team
13:00 | Workshop/Session 1 | Facilitators
14:30 | Break | Event Coordinator
15:00 | Panel discussion | Moderator & Panelists
16:30 | Closing remarks and wrap-up | Event Coordinator
17:00 | Event ends | All
17:30 | Breakdown and cleanup | Cleanup Crew
4. Vendor & Supplier Information
List all vendors and suppliers needed for the event.
Vendor/Supplier | Service Provided | Contact Info | Notes
Venue | Venue rental | (Phone/Email) | Contract signed? (Yes/No)
Catering | Food & beverage services | (Phone/Email) | Menu confirmed? (Yes/No)
AV/Tech Support | Audio-visual equipment setup | (Phone/Email) | Equipment confirmed? (Yes/No)
Decorations | Event decorations setup | (Phone/Email) | Final design confirmed?
Entertainment | Music/performers/speakers | (Phone/Email) | Arrival time confirmed?
Security | Security services | (Phone/Email) | Number of guards confirmed?
5. Marketing & Promotions Plan
Outline the strategy for promoting the event.
Marketing Channel | Description | Date | Responsibility | Status
Social Media (Instagram, FB) | Create posts and ads | MM/DD/YYYY | Marketing Team | In Progress
Email Invitations | Send invites to mailing list | MM/DD/YYYY | Coordinator | Completed
Website/Blog | Feature event on website | MM/DD/YYYY | Web Team | Not Started
Press Release | Publish press release | MM/DD/YYYY | PR Team | In Progress
Flyers/Posters | Distribute printed materials | MM/DD/YYYY | Volunteer Team | Completed
6. Logistics Checklist
Ensure all logistical items are accounted for.
Item | Details | Responsibility | Status
Permits | Event permits secured | Coordinator | Pending
Parking | Arrangements for guest parking | Venue Team | Completed
Transportation | Shuttle/transport for VIPs | Logistics Team | Pending
Security | Security measures in place | Security Team | Completed
Audio-Visual Equipment | Sound and video setup | AV Team | In Progress
Seating Arrangement | Chairs, tables, seating chart | Event Staff | Not Started
Signage | Directional and event signage | Volunteer Team | In Progress
First Aid | First aid station setup | Health & Safety Team | Completed
7. Staffing & Volunteer Plan
Assign key roles to staff or volunteers.
Role/Position | Name/Team | Contact Info | Shift Time
Event Coordinator | [Name] | (Phone/Email) | All day
Registration Desk Staff | [Name/Team] | (Phone/Email) | 9:00 AM - 12:00 PM
Setup Crew | [Name/Team] | (Phone/Email) | 7:00 AM - 9:00 AM
AV Technician | [Name/Team] | (Phone/Email) | 8:00 AM - 5:00 PM
Catering Staff | [Name/Team] | (Phone/Email) | 11:00 AM - 2:00 PM
Cleanup Crew | [Name/Team] | (Phone/Email) | 5:00 PM - 7:00 PM
8. Post-Event Evaluation
Use this section after the event to assess the success and areas of improvement.
Evaluation Criteria | Comments
Event Objectives Met? | (Yes/No, details)
Budget Adherence? | (Under/Over budget, why?)
Attendee Satisfaction? | (Feedback, survey results)
Vendor/Staff Performance? | (Any issues, things to note)
Logistics/Execution Challenges? | (Problems encountered, solutions)
Key Learnings for Future Events? | (Recommendations for improvement)